## Slide 1: Plan for Scanning-Day (Mar 16 2018)
Initially drafted by Jungwon & Kunwoo
Mar 15 2018

## Slide 2: Overview
Schedule on Mar 16 (Fri) 2018
  8:40 AM : Gathering at PSE Lobby
  8:40 - 12:00 : Arrangement & Scanning
  12:00 - 14:00 : Joining in Bruce's farewell party
  14:00 - 16:00 : Scanning
Participants
  ISSUM members: Pio, Yi-Chen, Afnan, Kang
  Indoor modeling expert: Kivanc
  Supporters: Jungwon, Kunwoo
Plan for Scanning
  Total 9 sets

## Slide 3: Scanning System
Optech Maverick Mobile Mapping System
  http://www.teledyneoptech.com/index.php/product/maverick/

## Slide 4: Comments (1/2)
Pio's comment on 'Set 7: Campus Walk'
  Some buildings (e.g. York lanes - Student Centre, Student Centre - Vari Hall) have short indoor paths connecting them. These are important for us.
Kivanc's comment for open space movement
  To make a turn from the area between chemistry and life science buildings might be preferred to capture a little pedestrian square to model the open space movements.

## Slide 5: Comments (2/2)
Kivanc's comment on scanning priority
  Scan Set 3, 4, 5, 6, and 7 could be set as priority, and then 8, 9 sample floors, and 1, 2 if time is tight.
Kivanc's comment on processing & file format
  Asking for preprocessing ? postprocessing?
  .las file?

## Slide 6: Plan for Scanning Set
Set Number | Place | Type
1 | York Blvd Outdoor Loop | All Outdoor Path
2 | South York Blvd Building Corridor Loop | Indoor + Outdoor Path
3 | Student Centre | Indoor + Outdoor Path
4 | York Lane | Indoor + Outdoor Path
5 | Vari Hall | All Indoor Path
6 | Ross Building | All Indoor Path
7 | Campus Walk | All Outdoor Path
8 | PSE Building | All Indoor Path
9 | Chemistry Building | All Indoor Path

## Slide 7: Set 1: York Blvd Outdoor Loop
All Outdoor Path
  Scanning the building wall outside.
Starting point
Outdoor path
Indoor path

## Slide 8: Set 2: South York Blvd Building Corridor Loop
Indoor + Outdoor Path

## Slide 9: Set 3: Student Centre
Indoor + Outdoor Path
  Including a corridor basically, and indoor space if possible

## Slide 10: Set 4: York Lane
Indoor + Outdoor Path
  Including all the corridors

## Slide 11: Set 5: Vari Hall
All Indoor Path
  Path: Not determined yet

## Slide 12: Set 6: Ross Building
All Indoor Path
  Path: Not determined yet

## Slide 13: Set 7: Campus Walk
All Outdoor Path

## Slide 14: Set 8: PSE Building
All Indoor Path
  Scanning all floors (B, G, 2, 3, 4)

## Slide 15: Set 9: Chemistry Building
All Indoor Path
  Scanning all floors (G, 2, 3, 4)

## Slide 16: Further Discussion
Issues for 8:40 AM (Mar 16) Meeting
  Priority & sequence for scanning
  Indoor Path for 'Set 5: Vari Hall', 'Set 6: Ross Building', 'Set 8: PSE Building', and 'Set 9: Chemistry Building'
  Principal accompanying people
    Originally plan - 8:40 AM: Kivanc, 10 AM: Pio, 11 AM: Kang, 2 PM: Yi-Chen, 3 PM: Afnan
    However, it should be changed as Afnan has to join in the Thales meeting (~ 3 PM or late).